## Slide 1: KY LEADS Collaborative
C3: Prevention & Early Detection

## Slide 2: Project Development Timeline (Original)
  Award: 19 Sep 2014
  KY Leads Leadership Mtgs
  C3 Leadership Mtgs
  11 Nov 2014 Press Conference
  C3 Project Team Mtgs
  Emerging Decisions & Standards
  Work-Group Assignments
  Database & Data Standards
  CMS Decision date 5 Feb 2015
  CMS Implementation conference call 11 Feb 2015
  Conference calls with Sites
  Work-Groups
  Database Platforms
  Data harmonization
  Study Synopsis
  Concept Feasibility
  CE Central Education Module Prep
  Guideline Development & Site Stratification
  Medical Advisory Board meeting 17 Jul 2015
  Continuum of Care manual and Tobacco Treatment Best Practice manual up for review
  Data Platform Evaluation finalized
  Data Dictionary Established
  Dissemination/Implementation research incorporated
Award & Announcement Initial Planning
1st Quarter
Project Development 2nd Quarter
Project Development 3rd Quarter
Project Development
4th Quarter

## Slide 3: Project Development Timeline (Deliverables)
  Study Synopsis
  Concept Feasibility
  Dissemination and Implementation Questions
  Site Visit Template
  Guidelines/Stratification of sites
  Checklist/ Site Visit Materials
  Project Communication Plan
  Navigator Listserv
  Continuum of Care manual
  Tobacco Treatment Best Practice Manual
  3rd Quarter deliverables
  CE Central Education Module Prep (resources, modules, outcomes)
  Stipend negotiation
  Marketing/External Communication Plan
  Database deliverables (dictionary, platform, testing)
  National conference presentation
  National Expert Consultant Visit
  Scholarly Manuscript
  KCP Regional Cancer Control Specialist presentation
  External advisory panel for consultation
Project Development 3rd Quarter- April-June
Deliverables for MAB meeting 17 Jul 2015
Project Development 4th Quarter July-September
Additional Deliverables

## Slide 4: Project Development Workgroup Assignments
Project Management: Tim Mullett, Jennifer Knight, Kris Damron, Trey Alexander
Clinical: Tim Mullett, Michael Brooks, Eric Bensadoun, Jamie Studts, Ellen Hahn, Trey Alexander (admin.), Angela Criswell (observer)
Education: Jennifer Knight, Ellen Hahn, Michael Brooks, Eric Bensadoun, Jamie Studts, Tim Mullett, Dana Lee, Amy Copeland, Angela Criswell, Kris Damron, Trey Alexander
Data Management: Eric Durbin, Tamas Gal, Bront Davis, Justin Levens, Lara Sutherland, Eric Bensadoun, Tim Mullett, Jennifer Knight, Kris Damron, Trey Alexander, Amy Copeland, Angela Criswell
Study Chairs: Tim Mullett, Jennifer Knight, Trey Alexander (admin.)

## Slide 5: Project Management Workgroup Priorities
7/1/15
  Site Visit Template
  Guidelines and Definitions around stratification of sites
  Checklist and Site Visit Materials
  Site Budget negotiation process defined
  Project Communication Plan
9/1/15
  National Conference Presentation
  National Expert Consultant Visit
  Scholarly Manuscript submission

## Slide 6: Data Management Priorities
Implementation and Dissemination Questions
Data Management Workgroup- led by Clinical Project Data Manager
Data Dictionary
  Evaluated CMS requirements (released 5 Feb 2015)
  Harmonized clinical data elements (ACR, KCR, NLST)
  Clinical core data dictionary
  Implementation core data dictionary - PRIORITY
Database Platform Evaluations
Preliminary Database Platform evaluation/testing
Final Dataset
Database build, testing, refinement, testing, finalize, release
9/1/15 (final testing)

## Slide 7: Clinical Workgroup Priorities
7/1/15
  Continuum of Care manual
  Tobacco Treatment Best Practice Manual

## Slide 8: Education Activities- Year 1
CE Central
Sohil Makwana- Preventative Medicine Resident SME Interviews
C3 Study Landing Page Sessions (8 planned):
  Radiology (Brooks)
  Screening Program Team (Mullett)
  Screening Navigator/Coordinator (Lee, Grindle)
  Shared Decision Making (Studts)
  Tobacco Addiction Treatment (Darville, Worth)
  Radon Prevention & Second-hand smoke (Hahn)
  Multidisciplinary workup and care (Bensadoun, ad hoc)
  Radiology followup (Brooks)
C3 Study Landing Page:
  Customized
  User log-in
  Certificate of Completion
  Certificate of Competency (minimum score required)
  eLearning Communities
  Polling questions

## Slide 9: Education Workgroup Priorities
7/1/15
  Secondhand smoke educational information
  Radon prevention educational information
  Lung Cancer awareness resources
  Continuing Education modules finalized
  Outcome measures and evaluation methods for education modules
9/1/15
  Marketing/External Communication Plan

## Slide 10: Study Chair Priorities
Deliverables for review by MAB meeting 17 Jul 2015:
  Continuum of Care manual
  Tobacco Treatment Best Practice Manual
  Guidelines and definitions around stratification of sites
  Education Session Outcomes
  Data Dictionary
  Database development/testing
  8/1/15
    Kentucky Cancer Program Regional Cancer Control Specialists
    External Advisory Panel of National Experts